## Sheet1
PROJECT CHARTER
Project Title | AI 2025 |  | Project Manager | Liz
Date | 2024-01-28 |  | Project Sponser | COMPANY
Project Description
Currently, the company operates with distinct forecasting tools and techniques across its two main business units, each managing its own forecasting team. The goal is to create a single, global AI tool that automates the forecasting of consumer demand based on historical and predicted sales volumes and trends.
Business Need
AI 2025 not only streamlines forecasting processes but also contributes to cost reduction, operational efficiency, and strategic goals, positioning the COMANY for sustained success in a dynamic market environment.
Risk and Issues
1. Bias and Discrimination 2. Unemployment and Economic Impact 3. Security and Privacy Concerns 4. Ethical Dilemmas 5. Data Quality and Availability 6. Integration Challenges
Work Plan
1. Project Initiation: Conduct a kick-off meeting with key stakeholders and review and finalize the project scope document, post that obtain formal approval from Liz and key stakeholders. 2. Planning and Strategy: Conduct a detailed analysis of AI technology requirements with TPZ and finalize the budget and timeline. 3. Pre-Implementation: Conduct a project Pre-Mortem and identify and document KPIs and Develop a detailed Project Charter 4. Implementation: Integrate the AI tool with existing systems and implement the cost reduction strategy 5. Post-Implementation: Address issues and challenges as they arise and optimize the AI tool based on user feedback. 6. Project Closure: Conduct a project review with key stakeholders and finalize and distribute project documentation and obtain formal project acceptance.
Project Team
Role |  | Name
Assoc CEO |  | Murat
Leadership |  | Helen
Project Manager |  | Liz
Project Sponsor |  | COMPANY
Technology Partner |  | TPZ Representatives
Timeline Milestone
Estimates |  | Plan | Develop | Test | Deploy
Taget Date |  | 2024-03-15 | 2024-07-22 | 2024-09-19 | 2024-12-20
Review Date
Completion date
Approvals
| Name |  |  | Signature | Date
Project Manager | Liz
Project Sponser | COMPANY